## Sheet1
Annex 7
Indicative time schedule of involvemeent of sel-governing regions into implementation of the ROP
Process | Entity | Indicative time schedule of involvement of self-governing regions into implementation of the ROP
|  | February | March | April | May | June | July | August | September |  | October | November | December
WG meetings
WG for ROP, Progr. Manual, Int. Manual etc. | MA + IBMA | [12 empty] | →
Analysis of the needs of IBMA
Acquisition of data and processing of data | Ext. counc.+ IBMA
Discussion of Final Report | MA + IBMA
Processing of result data on MA + IBMA | MA + IBMA
Internal Procedures Manual of IBMA for ROP
Guidance (structure, audit trails, etc.) | MA
1st version of Procedures Manual of IBMA | IBMA
1st stage of system auditu of MF SR | MA + IBMA + auditor
2nd stage of system audit at MF SR - arrangement of Manual | MA + IBMA + auditor
3rd stage - final statement of the MF SR audit | MA + IBMA + auditor
Final versions of Internal Procedures Manual of IBMA | MA + IBMA
Arrangement of organizational struct. of self-govern. regions | MA + IBMA
Administrative capacities of IBMA
Guidance of MA on administrative capacities of IBMA | MA
Recruitment of administrative capacities | IBMA | [12 empty] | →
Training and testing of administrative capacities of IBMA | MA + IBMA | [12 empty] | →
Certified minimum administrative capacities of IBMA | IBMA
Delegating powers on IBMA
Preparation and discussion on draft agreement | MA + IBMA
Approving and signing of agreement | MA + IBMA
Thematic delegating of powers on IBMA
Publicity and information | MA + IBMA
Receiving of applications | MA + IBMA | [12 empty] | →
Appraisal of applications | MA + IBMA | [12 empty] | →
Financing of projects | MA + IBMA | [8 empty] | Depending on implementation, estimated March 2008 |  |  |  | →
Control of acceptance and appraisal of projects | MA + IBMA | [12 empty] | →
Control of implementation of projects | MA + IBMA | [8 empty] | Depending on implementation, estimated March 2008 |  |  |  | →
Note 1: Given time schedule expects termination of negotiations in July, approval of ROP in September
Note 2: Course of the given stages can be different at every IBMA, depending on the readiness of individual IBMA
Expectation of start of implementation of indivi.measures acc.to activities |  | Publicity and information/ announing of Call |  | Receipt and appraisal / control of processes |  | Financing/ control of operations |  | Monitoring
Regeneration of settlements |  | November 2007 |  | January 2008 |  | May 2008 |  | July 2008
Regional communications ensuring transport serviceability of the regions |  | - |  | March 2008 |  | November 2008 |  | September 2008
Infrastructure of tourism |  | January 2008 |  | March 2008 |  | August 2008 |  | September 2008