## Sheet1
[10 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
| STEPS | TITLE / CONTENTS | OV NUMBER | CONVENOR | OFFICIAL PROJECT TEAM MEMBERS | No MEETINGS | No MEETINGS | COMMENTS / PROGRESS | ETAG N° | EC - SCC | EC - OV | SCC | EC | WP | WP | 1st draft | ExCom | SCC | EC letter | Languages | End
| WORKING GROUPS |  |  | SECRETARIAT |  | BUDGETED | ACTUAL |  |  | greenlight |  | Decision | letter | to | acceptance | to EC | Final ETAG | Opinion | endorsement | available | Coex,
[10 empty] | ETAG | (Step 0 OV) | FM - AC | FM | EC | EC | (Step 1 OV) | (Step 2 OV) |  | (Step 3 OV) |  | period
1 | Metal Anchors for Use in Concrete | Metal anchors for use in concrete | 93-02 | Mr K. Laternser - DIBt | Mr Gurney, BBA - Mr Blache, CSTB, | 10 WG / 10 PT | 11 WG / 9 PT | Will be finally refunded: 10.64 / 9 | 001 | 1: 22/23-4-93; 2: 1993-12-08; 3: 1996-03-25; 4: 1996-04-18; 5: 1996-06-28; 6: 1997-01-21
| Part 1: Anchors in General | Torque controlled, deform. controlled |  | Mr G. Feistel - DIBt | Mr Hordijk, SBK |  |  | Progress: Part 1-3: distribution final comments to TB | 001 | 3: (96/582); 7: 1994-03-23; 8: 1997-09-05; 9: 7/8-10-97; 10: 1997-10-29; 11: E,F,D,DK,I,H,Pl,CZ; 12: 7/02
| Part 2: Torque-controlled Expansion Anchors | Undercut anchors | [5 empty] | Part 4: delays possible? | 001 | 7: 1994-03-23; 8: 1997-09-05; 9: 7/8-10-97; 10: 1997-10-29; 11: E,F,D,DK,I,H,Pl, CZ; 12: 7/02
| Part 3: Undercut Anchors | [7 empty] | 001 | 7: 1994-03-23; 8: 1997-09-05; 9: 7/8-10-97; 10: 1997-10-29; 11: E,F,D,DK,I,H,Pl, CZ; 12: 7/02
| Part 4: Deformation-controlled Expansion Anchors | [7 empty] | 001 | 7: 1994-12-07; 8: 1998-09-03; 9: 6/7-10-98; 10: 1998-12-09; 11: E,F,D,DK,I,H,Pl, CZ; 12: 7/02
| Part 5: Bonded Anchors | Bonded anchors | [5 empty] | Part 5: time schedule normal? | 001 | 7: 1994-11-28; 8: 2001-06-12; 9: 12-13/12/01; 10: 2002-05-28; 11: E, F, D, H, Pl, CZ; 12: 02/05
| Progress file n°1 (Parts 1, 2, 4, 5 and annexes A, B and C) | [7 empty] | 001 | 7: -; 8: Febr 2006; 9: 23/06/2006
[17 empty] | am Nov 2006 | - | 08/03/2007 | E,D | ***
| Progress file n°2 (Part 5) | [7 empty] | 001 | 8: 06/07/2007; 9: X; 10: 2008-02-01; 11: E,D
| Progress file n°3 (Part 3) | [8 empty] | 8: X; 9: (02/03/2009)
| Progress file n°4 (Part 6) | [8 empty] | 8: X; 9: (02/03/2009)
| Progress file n°5 (Annex C) | [8 empty] | 8: 2008-03-13; 9: 2008-08-29; 10: (24/02/2009)
Progress file n°6
2 | Part 6: Metal Anchors for Use in Concrete for Fixing Lightweight Systems | Ceiling anchors | 95-02 | Mr K. Laternser - Mr Feistel, DIBt |  | 6 WG / 6 PT | 2 WG / 2 PT | Progress: normal | 001 | 1995-09-27 | 1995-12-20 | 1996-10-07 | 1996-12-06 | 1997-06-18 | 1997-10-03 | 1996-02-06 | 2003-02-27 | 13-14/05/03 | 2004-02-02 | E,D, H, Pl | 08/06
(97/161)
| Progress file | [8 empty] | 8: (X)
3 | Plastic Anchors for Use in Concrete and Masonry | Plastic anchors | 95-03 | Mr K. Laternser - Mr Feistel, DIBt | Mr Gurney, BBA - Mr Blache, CSTB, | 9 WG / 9 PT | 1 WG / 1 PT | Progress: normal | 020 | 1: 1995-09-27; 2: 1995-12-20; 3: 1996-11-20; 4: 1996-12-06; 5: 1997-06-18; 6: 1997-10-03; 7: 1996-02-06
| Part 1: General | [7 empty] | 020 | 3: (97/463); 8: 2004-06-04; 9: X; 10: 17/07/2006; 11: E,D; 12: 04/09
| Part 2: for use in normal weight concrete | [7 empty] | 020 | 8: 2004-06-04; 9: X; 10: 17/07/2006; 11: E,D; 12: 04/09
| Part 3: for use in solid masonry materials | [7 empty] | 020 | 8: 03/2005; 9: X; 10: 17/07/2006; 11: E,D; 12: 04/09
| Part 4: for use in hollow or perforated masonry | [7 empty] | 020 | 8: 03/2005; 9: X; 10: 17/07/2006; 11: E,D; 12: 04/09
| Part x: for use in lightweight aggregate concrete | [7 empty] | 020 | 8: (on hold); 9: (on hold)
| Part 5: for use in autoclaved aerated concrete | [7 empty] | 020 | 8: 03/2005; 9: X; 10: 17/07/2006; 11: E,D; 12: 04/09
| Part for ETICS | [7 empty] | 014 | 8: 2001-11-22; 9: 12-13/12/01; 10: 2002-01-16; 11: E,H, Pl,D, CZ,Sk; 12: 10/04
| Progress file | [8 empty] | 8: X; 9: (02/03/2009)
4 | Metal Injection Anchors For Use in Masonry | Injection anchors | 95-04 | Mr K. Laternser - Mr Feistel, DIBt | Mr Bruun, ETA-DK | 7 WG / 7 PT | 1 WG / 1 PT | Progress: delays on first draft, rest: normal | 029 | 1995-09-27 | 1995-12-19 | 1996-10-07 | 1996-12-06 | 1997-06-18 | 1997-10-03 | 29-02-98 | 25/03/2007 | (05/01/2009)
(97/177)
5 | Structural Sealant Glazing Systems (SSGS) | Part A: supported | 93-01 | Mr E. Dupont - CSTC | Mr Abraham, CSTB - Mr Lutz, DIBt - | 10 WG / 10 PT | 13 WG / 8 PT | Will be finally refunded: 12.508 / 9 | 002 | 22/23-4-93 | 1993-12-08 | 1996-03-25 | 1996-04-18 | 1996-06-28 | 1997-01-21
| Part 1: Supported and Unsupported Systems | Part B: non-supported |  | Ms E. Deforche | Mr Rutgers, SBK |  |  | Progress: finalisation June 1997 | '002 | [6 empty] | 23-03 28-11-94 | 1998-06-26 | 30-6 1-7-98 | 1998-09-24 | E, D, F,DK, H, Pl,CZ | 06/03
| Part 2: Coated Aluminium | Part E: coated Aluminium |  | Mr Dupont - Mr Galimberti -ICITE | Mr Lutz, DIBt - Mr Abraham, CSTB - Mr Haynes, BBA |  |  |  | '002 | 1995-12-19: 1997-06-26 | 1998-04-03 | 2001-11-22 | 12-13/12/01 | 2002-01-16 | E, F, D, H ,Pl,CZ | 10/04
| Part 3: Thermal Breaks | Part D: thermal break profiles |  | Mr Dupont - DIBt or CSTB? | Mr Lutz, DIBt - Mr Abraham, CSTB?- Mr Haynes, BBA |  |  | distributions of meetings to be fixed | '002 | 1995-12-19: 1997-06-26 | 1998-04-03 | X | 22-23/05/01 | 2002-05-28 | E,D, H, Pl, CZ | 02/05
| Part 4: Opacified Glazings | Part C: opacified glass |  | Mr Dupont - BBRI | Mr Lutz, DIBt - Mr Abraham, CSTB - Mr Haynes, BBA | 7 WG / 6 PT | 1 WG / ? PT | Progress: to be discussed | '002 | 1995-12-19: 1997-06-26; 1996-10-07: (96/582) | 1998-04-03 | (on hold) | (on hold)
| Progress file | [9 empty] | 21/12/2006 | - | - | - | - |  | X | 23/06/06
[17 empty] | X | (28/08/09)
6 | External Thermal Insulation Composite Systems/Kits with Rendering | External Thermal Insulation | 95-01 | Mr Ch. Lejeune - CSTB | Mrs Alexandersen, ETA-DK | 11 WG / 11 PT | 11 WG / 11 PT | Progress: pre-draft circulated | 004 | 1991-12-12 | 1995-09-25 | 1997-02-03 | 1997-02-12 | 1997-07-01 | 1997-12-04 | 1995-12-01 | 1999-11-16 | 9/10-12-99 | 2000-08-11 | E, D, F, H, Pl, CZ | 05/03
[10 empty] | 1996-10-07: (97/556) |  |  |  |  | Sk
| Progress file n°1 | [9 empty] | 21/12/2006 | - | - | - | - |  | 2008-05-16 | (05/01/2009)
| Progress file n°2 | Composite Systems | Internal No: 94.01 | Ms N. Blanchard - CSTB | Mr Blaisdale, BBA - Mr Terwindt, SBK |  |  | possible problems on mechanically fixed systems
7 | Non-loadbearing Permanent Shuttering Systems Based on Hollow Blocks | Systems kits for shuttering hollow | 96-04 | Mr B. Blache - CSTB | Mr Gurney, BBA - Dr Hartz, DIBt-Mr Schneider, | 10 WG / 10 PT | 3 WG / 2 PT | Progress: delay in first draft | 009 | 1996-04-30 | 1996-09-03 | 1997-06-10 | 1997-06-25 | 1997-12-09 | 1998-02-05 | 1998-01-29 | 2001-02-21 | 22-23/05/01 | 2002-05-28 | E,D, H, Pl,CZ | 02/05
| or Panels of Insulating Materials and sometimes, Concrete | blocks or plates |  | Mr Delmotte - CSTB | OIB |  |  |  |  | 1996-10-07: (98/279)
8 | Mechanically Fastened Flexible Waterproofing Systems | Mechanically fastened flexible | 96-01 | Mr T. Bruun - ETA-DK | Mr Kelly, BBA - Mr Lacroix, SECO - Mr Noreng, | 10 WG / 10 PT | 3 WG / 2 PT | Progress: normal | 006 | 1996-04-30 | 1995-07-30 | 1997-06-10 | 1997-06-25 | 1997-10-15 | 1997-12-19 | 1997-08-26 | 1999-11-16 | 9/10-12-99 | 2000-08-11 | E, F, D, H, Pl, CZ | 05/03
[10 empty] | 1996-10-07: (98/143) |  |  |  |  | Sk
| Progress file | [15 empty] | 06/07/2007 | (05/01/2009)
|  | waterproofing membranes |  | Mrs K. Alexandersen - ETA-DK | NBI
9 | Liquid Applied Waterproofing Kits | Liquid Waterproofing Systems | 96-03 | Mr S. Birkenfeld - SBK/KIWA | Mr Kelly, BBA - Mr Sartori, ICITE | 13 WG / 8 PT | 16 WG / 15 PT | Will be finally refunded: 13.456 / 12 | 005 | 1996-06-25 | 1996-09-03 | 25-26/03/98 | 1998-04-16 | 1998-06-30 | 1998-09-25 | 1996-02-03 | 1999-11-28 | 9/10-12-99 | 2000-08-11 | E,D, H, Pl, CZ | 05/03
[10 empty] | 1996-10-07: (98/559) |  |  |  |  | Sk
Progress file
10 | Internal Partition Kits | Internal Partition Systems | 96-02 | Mrs K. Alexandersen - ETA-DK | Mr Gurney, BBA - Mr Blache, CSTB - | 9 WG / 8 PT | 11 WG / 8 PT | Will be finally refunded: 10. / 8 | 003 | 1996-06-25 | 1996-08-30 | 7-8/10/97 | 1997-10-30 | 1998-01-19 | 1998-04-22 | 1998-02-17 | 1998-09-03 | 9-10/12/98 | 1999-02-05 | E, F, D, DK, H, Pl,CZ | 03/04
[10 empty] | 1996-10-07: (98/213) |  |  |  |  | Sk
| Progress file | [15 empty] | X | 23/06/06 | (WG-TB)
11 | Self-supporting Translucent Roof Kits | Self supported translucent roof kits | 96-05 | Mr B. Haynes - BBA | Mr Einsfeld (DIBt) - Mr Thoma (OIB) | 9 WG / 9 PT | 2 WG / 0 PT | Progress: normal | 010 | 1996-10-07 | 1997-01-15 | 25-26/03/98 | 1998-04-16 | 1998-06-30 | 1998-09-25 | 1998-01-29 | 21/02/2001 | 22-23/05/01 | 2002-09-24 | E,D,H, Pl | 08/06*
(98/600)
12 | Prefabricated Stairs Kits | Prefabricates stairs composed of | 96-06 | Mrs K. Riipola - VTT | Mr Laternser, DIBt - Mr Kohlmaier, OIB - | 8 WG / 10 PT | 2 WG / 0 PT | Progress: normal | 008 | 1996-10-07 | 1997-01-15 | 30/6 1/7/98 | 1998-09-30 | 1998-11-10 | 1998-12-07 | 1997-08-07 | 2000-05-18 | 12-13/12/01 | 2002-01-16 | E,D, H, Pl, CZ | 10/04
[10 empty] | 1996-10-07: (99/89) |  | 2001-06-12 |  |  | Sk
| Progress file | prefabricated steps |  | Mr A. Helenius - VTT | Mr Helland (NBI)
13 | Post-tensioning Systems for the Prestressing of Structures | [7 empty] | 013 | 1997-04-29 | 1997-09-26 | 1997-12-03 | 1998-04-16 | 1998-06-30 | 1998-09-24 | 1998-04-14 | 22/10/2001 | 12-13/12/01 | 2002-05-28 | E, H, Pl, D | 02/05
(98/456)
14 | Light Composite Woodbased Beams and Columns | [7 empty] | 011 | 7/8-10-97 | 1997-12-10 | 30/6 1/7/98 | 1998-09-30 | 1998-11-10 | 1999-01-13 | 1998-08-21 | 2001-06-12 | 12-13/12/01 | 2002-01-16 | E, F, D, H, Pl | 10/04
(99/92)
15 | Timber Frame Building Kits | [7 empty] | 007 | 2/3-12-97 | 1998-09-02 | 6-7/10/98 | 1998-11-09 | 1999-10-29 |  | 1998-09-28 | 2000-05-18 | 12-13/12/00 | 2001-08-24 | E,D,DK, H, Pl, CZ | 05/04
(99/455)
| Progress file | [15 empty] | 2009-12-04 | (18/01/2010)
16 | Log Building Kits | [7 empty] | 012 | 2/3-12-97 | 1999-11-22 | 6-7/10/98 | 1998-11-09 | 1999-10-29 |  | 2000-11-28 | 2001-06-12 | 12-13/12/01 | 2002-05-28 | E,D, H, Pl,Sk | 02/05
(99/455)
Progress file
17 | Fire Stopping, Fire Sealing and Fire Protecting Products (**) | [8 empty] | 1996-10-07: (99/454)
| 1. Fire Stopping and Fire Sealing Products | [7 empty] | 026 | 30/6 1-07-98 | 1999-01-18 | 6-7/10/98 | 1998-11-09 | 2000-02-25 |  | 2000-12-22 | December 2006
| Part 1: General | [7 empty] | 026 | [7 empty] | 09/06/06 | 11/05/07 | 01/01/2008 | E, D
| Part 2: Penetration seals | [7 empty] | 026 | [7 empty] | 09/06/06 | 11/05/07 | 01/01/2008 | E, D
| Part 3: Linear Joint and Gap seals | [7 empty] | 026 | [7 empty] | 13/11/2006 | X | 01/02/2008 | E, D
| Part 4: Air transfer grilles | [7 empty] | 026 | [7 empty] | 13/07/2008 | (05/01/2009)
| Part 5: Cavity barriers | [7 empty] | 026
[10 empty] | 2 | 5 | 7 | 8 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19
| STEPS | TITLE / CONTENTS | OV NUMBER | CONVENOR | OFFICIAL PROJECT TEAM MEMBERS | No MEETINGS | No MEETINGS | COMMENTS / PROGRESS |  | EC - SCC | EC - OV | SCC | EC | WP | WP | 1st draft | ExCom | SCC | EC letter | Languages | End
| WORKING GROUPS |  |  | SECRETARIAT |  | BUDGETED | ACTUAL |  |  | greenlight |  | Decision | letter | to | acceptance | to EC | Final ETAG | Opinion | endorsement | available | Coex,
[10 empty] | ETAG | (Step 0 OV) | FM - AC | FM | EC | EC | (Step 1 OV) | (Step 2 OV) |  | (Step 3 OV) |  | period
| 2. Fire Protective Products | [7 empty] | 018 | 30/6 1-07-98 | 1999-01-18 | 6-7/10/98 | 1998-11-09 | 2000-02-25 | 2005-03-29 | 2000-12-22
| Part 1: General | [7 empty] | 018 | [7 empty] | 27/02/04 | 2004-04-02 | 2004-09-21 | E, D | 06/07
| Part 2: Reactive coatings | [7 empty] | 018 | [7 empty] | 27/10/05 | X | 17/07/2006 | E, D | 04/09
| Part 3: Renderings | [7 empty] | 018 | [7 empty] | 01/12/05 | 1702/2006 | 03/03/2006 | E,D | 11/08
| Part 4: Board, slab, and mat products and kits | [7 empty] | 018 | [7 empty] | 27/02/04 | 2004-04-02 | 2004-09-21 | E, D | 06/07
| Progress file Part 4 | [7 empty] | 018 | [7 empty] | X | 2006-06-23
[17 empty] | am 18/12/06 | 2008-08-29 | (26/05/2009)
Progress file Part 2
| Progress file Part 3 | [15 empty] | 14/11/2009
| 3. Fire Retardant Products | [7 empty] | 028 | 1995-12-19: 19/12/2003 | 2004-05-18 | 14-15/03/2007 | 2008-08-29 | (24/02/2009)
18 | Prefabricated Wood-based Load-bearing Stressed Skin Panels | [7 empty] | 019 | 6-7/10/98 | 1999-01-18 | 30/06/1999 | 1999-07-13 | 2000-08-29 | 2001-07-31 | 2000-12-22
(2000/147)
[17 empty] | 27/02/2004 | 2004-04-02 | 2005-01-25 | E, CZ | 11/07
19 | Self-supporting Composite Light Weight Panels | [7 empty] | 016 | 6-7/10/98 | 1999-11-22 | 30/06/1999 | 1999-07-13 | 2000-08-29 | 2001-07-31
| Part 1: General | [7 empty] | 016 | 1996-10-07: (2000/147) | 2000-12-22 | 27/02/2003 | 13-14/05/03 | 2004-02-09 | E, Pl,D, CZ | 11/06
| Part 2: for use in Roofs | [7 empty] | 016 | [6 empty] | 2000-11-10 | 27/02/2003 | 13-14/05/03 | 2004-02-17 | E, Pl,D, CZ | 11/06
| Part 3: for use in external walls and claddings | [7 empty] | 016 | [7 empty] | 27/02/2004 | 2004-10-26 | 2005-03-02 | E,D | 12/07
| Part 4: for use in internal walls and ceilings | [7 empty] | 016 | [7 empty] | 4/06/2004 | 2004-10-26 | 2005-03-02 | E,D | 12/07
20 | Expansion joints for road bridges | [7 empty] | 032 | 9-10/12/98 | 1999-11-22 | 4-5-/07/2000 | 2000-10-02 | 2001-09-21 | 2004-10-21 | 2001-12-03
| Part 1: General | [8 empty] | 1996-10-07: (2001/19) |  | 13/03/2007 | (EC)
Part 2: Burried Expansion joints
Part3: Flexible Plug Expansion joints
Part4: Nosing Expansion joints
Part5: Mat expansion joints
Part 8: Modular expansion joints
21 | Three-dimensional Nailing Plates | [7 empty] | 015 | 9-10/12/98 | 1999-11-22 | 1999-04-08 | 1999-05-28 | 1999-06-30 | 1999-09-22 | 2000-09-07 | 2002-06-13 | 10-11/09/02 | 2002-09-24 | D,E, H, Pl,Sk | 08/07*
(97/638)
Progress file
22 | Vetures (prefabricated) Insulation Kits and Cladding Kits
| 1. Vetures | [7 empty] | 017 | 9-10/12/98 | 1999-11-22 | (2001/308) | 2000-10-02 | 2001-02-14 | 2001-07-31 | 2001-02-08 | 2003-10-23 | 2005 | 16/12/2005 | E, CZ, Sk, D | 09/08
4-5/07/2000
| 2. Kits for exterior Wall Claddings | [7 empty] | 034 | 12-13/12/00 | 2001-12-17 | (2003/640) | 2003-03-17 | 2003-07-02 | 2004-09-07 | 18/11/2004 | December 2006
| Part 1: Ventilated cladding elements and associated fixing devices | [8 empty] | 1996-10-07: 2003-09-04 |  | 27/03/2008 | 2008-08-29 | (25/05/2009)
| Part 2: Kits made of skin, the mechanical fixing devices and a specific subframe | [15 empty] | 27/03/2008 | 2008-08-29 | (25/05/2009)
Part 3: Kits made of skin glued to the subframe
23 | Falling Rock Protection Kits | [7 empty] | 027 | 4-5/7/00 | 2001-01-15 | (2003/728) | 2003-02-03 | 2004-01-29 | 2004-03-04 | 2001-12-03 | 09/06/2006 | X | 01/02/2008 | E
2003-10-03
24 | Prefabricated Industrial and Commercial Buildings | [7 empty] | 023 | 4-5/7/00 | 2001-01-15 | (2003/728) | 2003-02-03 | 2003-07-02 | 2005-03-02 | 2001-12-03 | December 2005 | X | 2006-09-19 | E | ***
[12 empty] | 2003-10-03 |  | am 23/02/05
25 | Liquid applied Bridgedeck Waterproof Kits | [7 empty] | 033 | 4-5/7/00 | 2001-01-15 | (2003/722/EC) | 2003-02-03 | 2003-07-02 | 2004-09-07 | 2003-10-12 | 11/03/2008 | 2008-08-29 | (24/02/2009)
2003-10-03
26 | Concrete & Metal Frame Building Kits
| 1. Concrete frame Building Kits | [7 empty] | 024 | 4-5/7/00 | 2001-01-15 | (2003/728) | 2003-02-03 | 2004-06-14 | 2005-03-11 | 2001-12-03 | December 2005 | X | 2006-07-28 | E | 04/09
| 2. Metal frame Building Kits | [7 empty] | 025 | 4-5/7/00 | 2001-07-16 | 2003-10-03 | 2003-02-03 | 2004-06-14 | 2005-03-11 | 2001-12-03 | December 2005 | X | 2006-07-28 | E | 04/09
27 | 1. Kits for Prefabricated Cold Storage Rooms | [7 empty] | 021 | 4-5/7/00 | 2001-01-15 | (2003/728) | 2003-02-03 | 2003-07-02 | (07/09/04) | 2001-12-03 | 2004-10-20 | X | 16/11/2005 | E, CZ,D | 08/08
[12 empty] | 2003-10-03 |  | am 16/02/05
| 2. Kits for Prefabricated Cold Storage Buildings and envelopes | [7 empty] | 021 | 4-5/7/00 | 2002-12-23 | 2004-10-26 | 2005-02-11 | 2005-02-16 |  | March 2003 | 03/2005 | X | 16/11/2005 | E, CZ, D | 08/08
(2005/484)
| Progress file | [9 empty] | 21/12/2006 | - | - | - | -
28 | Dowels for Structural Joints (previously called "Pins") | [7 empty] | 030 | 12-13/12/00 | 2001-12-17 | (2003/639) | 2003-03-17 | 2003-07-02 | (07/09/04) | 01/09/2003
[12 empty] | 2003-09-04 |  | am 08/09/06 | (WG)
29 | Watertight coverings for bathroom walls and floors | [7 empty] | 022 | 22-23/05/01 | 2001-12-17 | (2003/655) | 2004-03-11 | 2004-06-14 | 2005-03-11 | December 2002
| Part 1: Liquid applied waterproofing kits | [7 empty] | 022 | 1996-10-07: 2003-09-12 |  | 27/10/2005 | X | 20/07/2007 | E | ***
| Part2: Kits with flexible sheets with welded joints | [15 empty] | 13/11/2006 | (05/01/2009)
| Part3: Kits of inherently watertight boards | [15 empty] | 11/03/2008 | 2008-08-29 | (24/02/2009)
30 | Ultra thin Layer Asphalt Concrete | [7 empty] | 035 | 18-19/12/01 | 2002-12-23 | (98/601) | 16/12/2005 | 2006-07-10 |  | September 2003 | 19/07/2008 | (05/01/2009)
[12 empty] | 24/10/1998? |  | am 13/10/06 | 25/01/2007
31 | Inverted Roof Insulation Kits | [7 empty] | 031 | 10-11/9/02 | 2003-12-19 | (97/556) | 03/11/2006 | 19/02/2007
[12 empty] | 1997-08-20 |  | am 19/07/2007 | 17/02/09
| Part 1: General | [7 empty] | 031 | [6 empty] | 23/03/2004 | 13/03/2007 | (05/01/2009)
| Part 2: Rendered Insulation Products | [7 empty] | 031 | [6 empty] | 29/03/2005 | 2007-07-05 | (05/01/2009)
*: date as published by the EC (has to be amended)
**: one mandate resulting in three guidelines
***: no longer mentioned by the EC services
latest activity